## Sheet1
Lofthus frukt og saft - Gantt Chart
[5 empty] | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
Task | Start date | Days | End date | Responsible
Initial meeting | 2019-01-07 | 1 | 2019-01-08 | Project manager, Content specialist, Designer
Sign contract | 2019-01-07 | 1 | 2019-01-08 | Project manager
Research | 2019-01-08 | 5 | 2019-01-13 | Project manager, Content specialist, Designer
Strategic planning | 2019-01-11 | 10 | 2019-01-21 | Project manager, Content specialist, Designer
Branding | 2019-01-15 | 3 | 2019-01-18 | Project manager, Designer
Analyze competitors | 2019-01-17 | 3 | 2019-01-20 | Project manager, Designer
Target audience personas | 2019-01-19 | 2 | 2019-01-21 | Project manager, Designer
Customer meeting | 2019-01-21 | 1 | 2019-01-22 | Project manager, Content specialist, Designer
Content planning | 2019-01-21 | 2 | 2019-01-23 | Content specialist
Site planning | 2019-01-23 | 3 | 2019-01-26 | Content specialist, Designer, Frontend developer
Plan webshop solution | 2019-01-26 | 2 | 2019-01-28 | Content specialist, Designer, Frontend developer
Determine navigation | 2019-01-28 | 2 | 2019-01-30 | Designer, Frontend developer
Sitemap | 2019-01-30 | 2 | 2019-02-01 | Designer, Frontend developer
Styletile | 2019-02-01 | 2 | 2019-02-03 | Designer
Photoshooting | 2019-02-01 | 3 | 2019-02-04 | Photographer
Content development | 2019-02-02 | 3 | 2019-02-05 | Content specialist
Mockup | 2019-02-05 | 1 | 2019-02-06 | Designer
Customer meeting | 2019-02-06 | 1 | 2019-02-07 | Project manager, Content specialist, Designer
Site building | 2019-02-06 | 10 | 2019-02-16 | Frontend developer, Backend developer
UX testing | 2019-02-13 | 2 | 2019-02-15 | Content specialist, Designer
Browser and device testing | 2019-02-16 | 3 | 2019-02-19 | Frontend developer, Backend developer
Refinement | 2019-02-19 | 2 | 2019-02-21 | Project manager, Desiger, Frontend developer
Customer meeting | 2019-02-21 | 1 | 2019-02-22 | Project manager, Content specialist, Designer
Launching | 2019-02-22 | 1 | 2019-02-23 | Project manager
Formulas:
End date = SUM([Start date])+[Days]